## Project A
Project Name |  | Project A
Client Name |  | PT. Sakura System Solutions
Client Address |  | HDI Hive Menteng
Client Phone |  | 87873766464
Client Email |  | muhammadnaufalfm@gmail.com
No | Module Code | Module Name | Function Code | Function Name | Phase | PIC Username | Start Date | End Date
1 | FMW | Framework | FMW001 | Code First Setup | Design | yogayoga | 2017-08-07 | 2017-08-08
2 | FMW | Framework | FMW001 | Code First Setup | Implementation | yogayoga | 2017-08-08 | 2017-09-08
3 | FMW | Framework | FMW001 | Code First Setup | Testing | yogayoga | 2017-09-08 | 2017-09-10
4 | FMW | Framework | FMW002 | Basic GUI Template | Design | yogayoga | 2017-08-08 | 2017-08-09
5 | FMW | Framework | FMW002 | Basic GUI Template | Testing | yogayoga | 2017-08-09 | 2017-08-11
6 | FMW | Framework | FMW003 | Database Migration | Design | yogayoga | 2017-08-12 | 2017-08-13
7 | FMW | Framework | FMW003 | Database Migration | Implementation | yogayoga | 2017-08-13 | 2017-09-13
8 | FMW | Framework | FMW003 | Database Migration | Testing | yogayoga | 2017-09-13 | 2017-09-15
9 | FMW | Framework | FMW004 | Areas | Design | yogayoga | 2017-08-16 | 2017-08-16
10 | ORG | Organization | ORG001 | Company | Design | yogayoga | 2017-08-18 | 2017-08-20
11 | ORG | Organization | ORG002 | Employment Type | Design | yogayoga | 2017-08-21 | 2017-08-23

## Sheet1
2017-09-07 | 2017-10-07 | 30